## Slide 1: DGLVR Advanced Admin Training
PA State Conservation Commission
Sherri Law & Andy Mickey
Dirt, Gravel, and Low Volume Road Program
Notes: Purpose today: Provide detailed guidance on how to make sure projects turn out well. Will review full project lifecycle.

## Slide 2
Outline
Introductions
Policy Review Trivia Game
Intro to Project Management
Pre-application & application
Project administration: contracting through construction
Project completion

## Slide 3
Introductions
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Go around the room and say:
What CD/organization are you from?
What is your job title/role in the DGLVR Program?
How many years have you been there?

## Slide 4
Outline
Introductions
Policy Review Trivia Game
Intro to Project Management
Pre-application & application
Project administration: contracting through construction
Project completion
Click this link to launch trivia game:
DGLVR Policy Review - Advanced Admin Training - Custom Trivia Quiz Maker

## Slide 5
Outline
Introductions
Policy Review Trivia Game
Intro to Project Management
Pre-application & application
Project administration: contracting through construction
Project completion

## Slide 6
Project Management
Discussion:
What is “Project Management”?

## Slide 7
Project Management
Definition:
The art of bringing together a team to successfully complete a project
What does a project manager do?
A project manager leads their team through all phases of a project lifecycle
Not necessarily the direct manager/supervisor of all team members
Responsible for guiding team members and making sure they get the support they need
https://www.forbes.com/advisor/business/what-is-project-management/
https://shaggiuk.blogspot.com/2014/02/herding-cats.html

## Slide 8
Project Management
What does a project manager do?
Bring people together to meet a goal
  Plan and organize
  Break overall goal into smaller tasks
  Prioritize and delegate tasks
  Set timelines
  check in to make sure tasks are being completed in a timely manner
  Break down barriers to help team accomplish tasks
  Facilitate communication between team members
https://tse4.mm.bing.net/th/id/OIP.7S_bVOyRY9FCR1SY1vNbeQHaHa?w=630&h=630&rs=1&pid=ImgDetMain
Notes: Baking example: The project manager writes or at least follows the recipe, and makes sure all kitchen helpers are doing the right thing at the right time

## Slide 9
Why talk about Project Management?
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Discussion:
Why talk about project management?

## Slide 10
Why talk about Project Management?
To complete road projects as smoothly as possible!
Better Roads, Cleaner Streams
Notes: CD staff are project managers for DGLVR projects

## Slide 11
Project Management
Project:
Temporary endeavor undertaken to create a unique product, service, or result
https://www.pmi.org/about/what-is-a-project

## Slide 12
Project Management
Project:
Temporary endeavor undertaken to create a unique product, service, or result
https://www.pmi.org/about/what-is-a-project
Has a start, end, and specific timeline

## Slide 13
Project Management
Project:
Temporary endeavor undertaken to create a unique product, service, or result
https://www.pmi.org/about/what-is-a-project
Defined set of deliverables
Has a start, end, and specific timeline

## Slide 14
Project Management
Project:
For the DGLVR Program:
  Improve a certain section of road
  With specific ESM practices
  According to a planned budget
  In a set amount of time

## Slide 15
Project Management
Project:
For the DGLVR Program:
  Improve a certain section of road
  With specific ESM practices
  According to a planned budget
  In a set amount of time
  All defined in the DGLVR contract
  and attachments

## Slide 16
Project Management
Who is involved in DGLVR projects?
Conservation District
Road Owner
  Elected officials
  Road master/supervisor
  Road crew
Contracted construction crew
Engineer
Adjacent landowners
Solicitor
Other funding sources

## Slide 17
Project Management
Who is involved in DGLVR projects?
Conservation District
Road Owner
  Elected officials
  Road master/supervisor
  Road crew
Contracted construction crew
Engineer
Adjacent landowners
Solicitor
Other funding sources
Who is the project manager?

## Slide 18
Project Management
Who is involved in DGLVR projects?
Conservation District
Road Owner
  Elected officials
  Road master/supervisor
  Road crew
Contracted construction crew
Engineer
Adjacent landowners
Solicitor
Other funding sources
Who is the project manager?
The Conservation District knows how to successfully complete a DGLVR Project better than anyone else

## Slide 19
Additional Resources
Project Management Institute
  Home of Project Management | Project Management Institute
Google Foundations of Project Management
  Project Management Certificate & Training - Grow with Google

## Slide 20
Project Management
Overall goal: build an environmentally sensitive road
How to get from before to after?

## Slide 21
Project Management
Break up the overall goal into smaller steps
Put the steps in order (Prioritize and/or chronological order)
Set timelines & deadlines for each step
Identify tasks needed to complete each step
Assign team members to complete each task
Hold people accountable to completing their task correctly and on time
Throughout each step, offer support as needed to team members

## Slide 22
Project Management
Break up the overall goal into smaller steps
Put the steps in order (Prioritize and/or chronological order)
Set timelines & deadlines for each step
Identify tasks needed to complete each step
Assign team members to complete each task
Hold people accountable to completing their task correctly and on time
Throughout each step, offer support as needed to team members
There is a template for DGLVR Projects

## Slide 23
Project Life Cycle
DGLVR Project Life Cycle Checklist
Blank Forms - Center for Dirt and Gravel Road Studies (psu.edu)

## Slide 24
Project Life Cycle
Education and outreach
Pre-application meeting
Receive & review application
QAB meeting
CD Board meeting
Contracting
Preparing for Construction
  If applicable: Design, permitting, bidding
  Pre-construction meeting
Construction
Completion

## Slide 25
Project Life Cycle
Task | Who is involved
Education and outreach | CD Staff
Pre-application meeting | CD Staff, road owner, designer/engineer
Receive & review application | CD Staff
QAB meeting | CD Staff, QAB
CD Board meeting | CD Staff, CD Board
Contracting | CD Staff, road owner
Additional design / engineering | Road owner, engineer/consultant, CD staff
Permitting | Road owner, engineer/consultant, CD staff
Bidding | Road owner, engineer/consultant, CD staff
Pre-construction meeting | Road owner, road crew and/or contractor, engineer/consultant, CD staff
Construction | Road owner, road crew and/or contractor, engineer/consultant, CD staff
Final Inspection | Road owner, road crew and/or contractor, engineer/consultant, CD staff
Completion Report | CD staff, road owner

## Slide 26
Key to successful DGLVR Projects:
Communication
More district involvement throughout the project lifecycle
=
better projects
Project Management

## Slide 27
Effective Communication
https://en.wikipedia.org/wiki/File:Happy_Man_Throwing_Money_Cartoon.svg
Information
There are 2 parties in any communication
You can only control your side of the conservation, but it’s important to be aware of both
Notes: Communication is conveying information from one person to another
2 parts: sending and receiving
Needs to be conveyed in an understandable way
Audience needs to be receptive *** this is key and we often forget this part

## Slide 28
Effective Communication
Know your audience
What does the road owner care about?
Start with why, not what
Explain how you can solve a problem for your audience
https://en.wikipedia.org/wiki/File:Happy_Man_Throwing_Money_Cartoon.svg

## Slide 29
Effective Communication
Know your audience
What does the road owner already know?
Consider word choice
  Define any terms your audience may not be familiar with
Don’t assume program participants already know DGLVR details
  Provide all of the info they will need

## Slide 30
Effective Communication
Building trust helps the working relationship
  Listen
  Be reliable
    Complete tasks you commit to
    Follow up in a timely manner
  Be honest
    Connect them to additional resources when you don’t know the answer

## Slide 31
Effective Communication
Short and direct:
  Be clear about the most important points you’re trying to communicate
  Don’t take too long to get there or provide too much detail
Summarize key points
  Ask your audience to explain what they learned to confirm you’re on the same page
  End conversations by reviewing what the next step is and who needs to do what

## Slide 32
Effective Communication
Written Communication:
Provide information for future reference in a written format
Present information in an organized and visually appealing way
  Use bullet points
  Use different fonts, color, bold/underline, etc.
  Use pictures

## Slide 33
Use visual aids whenever possible
Example projects
ESM practices
What landowners can expect from a project
Project sketches
Diagrams and construction details
And more!
Effective Communication

## Slide 34
Technical Bulletins
Standard Detail Sheets
ESM Field Guide
Stream Continuity Flyers
Flyers for potential grant applicants
Annual Summary Reports
Tools – Visual Aids

## Slide 35
Effective Communication

## Slide 36
Project Life Cycle
Education and outreach
Pre-application meeting
Receive & review application
QAB meeting
CD Board meeting
Contracting
Preparing for Construction
  If applicable: Design, permitting, bidding
  Pre-construction meeting
Construction
Completion
Notes: Not going to talk in detail about education and outreach since there are recorded webinars and we just talked about communication tips in general

## Slide 37
Project Life Cycle
Recorded webinar: January 16, 2025: Education and Outreach Ideas for CDs
  With constant municipal turnover, education and outreach at the District level is a vital component of the Program. This webinar built on material presented at the 2024 workshop, and provided ideas, tips, and tricks learned from CDs.
  Webinar Download (74.3 MB): MP4 format (~44 minutes)
  Presentation Downloads:
    Adobe PDF (4.09 MB)
    MS Powerpoint (7.85 MB)
Flyers for Outreach
  DGLVR Handout for New Participants: This 2-page flyer provides a brief overview and introduction to the DGLVR Program.
  Example DGLVR Projects: This 2-page flyer shows example before and after pictures of completed DGLVR projects and frequent issues addressed by the DGLVR Program.

## Slide 38
Why talk about Project Management?
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Discussion
Education & Outreach
Now’s the time to show any educational materials you brought to share, ask for feedback, etc.
Discussion: communication and education tips and tricks?
  Types of education events
  Outreach to solicit program participation & pre-application meetings

## Slide 39
Outline
Introductions
Policy Review Trivia Game
Intro to Project Management
Pre-application & Application
Project Administration: Contracting through Construction
Project Completion

## Slide 40
Project Life Cycle
Education and outreach
Pre-application meeting
Receive & review application
QAB meeting
CD Board meeting
Contracting
Preparing for Construction
  If applicable: Design, permitting, bidding
  Pre-construction meeting
Construction
Completion

## Slide 41
Tools - checklists
Checklists available on Blank Forms - Center for Dirt and Gravel Road Studies (psu.edu)
  DGLVR Project Life Cycle
  Pre-application meeting
  Bid package review
  Pre-construction meeting
Remember – stream crossing projects have a separate set of checklists:
  Stream Crossing - Center for Dirt and Gravel Road Studies (psu.edu)

## Slide 42
Prep for Pre-application meeting
Review meeting checklist before the site visit
  Checklist is not all-inclusive of policy manual: refresh as needed
  Reach out to Center/SCC with questions

## Slide 43
Prep for Pre-application meeting
Learn about the road owner
  Review who, if anyone, is ESM Certified for the road owning entity you’re visiting
  When does their ESM Cert expire?
  What was the last project they completed?
https://dirtandgravel.psu.edu/education-training/course-attendance-tracker/

## Slide 44
Prep for Pre-application meeting
Research potential sites before visit, if possible
  Directions
  Print a map of municipal road(s) to reference during meeting
    Imagery, topography, roads
    Location of streams, potential sites, past projects
  Look up stream info
    Wetness index & StreamStats show more channels than stream layer
    Use StreamStats to delineate drainage areas
  Chapter 93 & trout stream status, impairments
  Soils, landowners, traffic data, etc.

## Slide 45
Prep for Pre-application meeting
Steer the road owner to their best potential sites
  Review roads ahead of meeting
    Proximity to resource, quality of resource, likelihood of environmental impact
  Discuss sites with road owner
  Visit multiple sites and narrow down from there
  You want to give your district good sites to select from and give the road owner their best chance of receiving funding.

## Slide 46
Prep for Pre-application meeting
Bring paperwork and field supplies

## Slide 47
Pre-application meeting
During the meeting, use the checklist to guide conversation (covers 3 main topics)
Program Outreach
  Program goals
  Focus on reduced maintenance benefits
Eligibility
  Site and applicant
  Steer applicants towards good projects and ESM practices
Project design
  Site diagnostic
  ESM practices

## Slide 48
Pre-application meeting
Determine a potential start and end point for the project.
  Focus on the segment length that is most likely to rank.
  Record coordinates or a landmark so the stationing can be recreated when needed.
  Wheel the road with the road owner to create a plan to address the existing issues. Record stations of proposed ESM practices and existing drainage features.
    Both parties should record the plan.
  Keep all issues in mind and what is needed to create a comprehensive project that reduces environmental impact and maintenance.
  Drainage disconnection, infiltration, detention, stabilization

## Slide 49
Pre-application meeting
Site Diagnostics
What does the site need?
If difficult, reach out to the Center for technical assistance
An engineer may be necessary for some projects
  Landslides, stream crossings, stormwater BMPs, etc.
  Important for including engineering in grant request
If you want to do something outside the box, contact the SCC

## Slide 50
Pre-application meeting
Multiple pre-app meetings may be needed
Make sure you get enough information for the application and/or ranking
  Stationing
  Create work plan
  Get enough info to estimate quantities
    Measurements in all 3 dimensions
  Take pictures
Length
Width
Depth

## Slide 51
Pre-application meeting
After the pre-application meeting:
Type up the workplan*
Material and Cost Estimating
  Estimate materials to provide to the road owner
  Estimate costs (don’t forget engineering) to get a realistic idea as to if the entire project can be done under one contract or if the site length needs to be reduced or the project needs to be phased Can the applicant complete the scope under one contract in a reasonable amount of time?
    Reducing scope vs. phasing should be based on project quality. Staff should steer this conversation with the road owner.
  Where will materials come from? What type of material is best?
  Get to know your quarries and material suppliers.

## Slide 52
Pre-application meeting
Follow up with the road owner
  Answer any questions not answered during the meeting
  Provide notes/sketch/tech bulletins/standard drawings/etc.
  Tell them their next step
  Set due dates
    Schedule follow up meeting
    Remind them of grant application deadline
    Send ESM training registration link

## Slide 53
Project Life Cycle
Education and outreach
Pre-application meeting
Receive & review application
QAB meeting
CD Board meeting
Contracting
Preparing for Construction
  If applicable: Design, permitting, bidding
  Pre-construction meeting
Construction
Completion

## Slide 54
Reviewing Applications
Remote Learning Center
Filling out grant application paperwork (92.4 MB) (~43 minutes) Intended audience: Potential Applicants (and CD staff). This presentation walks through how to fill out the grant application paperwork.
Reviewing grant applications (98.5 MB) (~53 minutes) Intended audience: Conservation Districts. This presentation explains what conservation districts should do after DGLVR grant applications are received and before the QAB meeting where applications are ranked.
Better Grant Applications (75.6 MB) (~47 minutes) This webinar discussed some common shortcomings of grant applications from applicants and considerations for improvement. (1/2023)

## Slide 55
Example Site: Dogtown Road, Genesee Twp

## Slide 56
Example Site: Dogtown Road, Genesee Twp

## Slide 57
Example Site: Dogtown Road, Genesee Twp

## Slide 58
Example Site: Dogtown Road, Genesee Twp

## Slide 59
Example Site: Dogtown Road, Genesee Twp

## Slide 60
Example Site: Dogtown Road, Genesee Twp

## Slide 61
Example Site: Dogtown Road, Genesee Twp

## Slide 64
Example Site: Dogtown Road, Genesee Twp

## Slide 65
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Activity
Application Review
You are the conservation district that received an application for Dogtown Rd.
Review the application for eligibility, meeting DGLVR requirements, and consistency with the pre-app meeting
Compile a list of questions/comments for the township

## Slide 67
Example Site: Dogtown Road, Genesee Twp

## Slide 69
Example Site: Dogtown Road, Genesee Twp

## Slide 70
Example Site: Dogtown Road, Genesee Twp

## Slide 71
Example Site: Dogtown Road, Genesee Twp

## Slide 72
Example Site: Dogtown Road, Genesee Twp

## Slide 73
Outline
Introductions
Policy Review Trivia Game
Intro to Project Management
Pre-application & application
Project administration: contracting through construction
Project completion

## Slide 74
Ranking and Contracting
County Conservation District
Quality Assurance Board
Conservation District Board
County Conservation District
Grant Application
Contract
Notes: Briefly remind audience of procedure to fund contracts. This is covered in detail in basic admin training. Answer any questions but otherwise move on quickly.

## Slide 75
Ranking and Contracting
County Conservation District
Quality Assurance Board
Conservation District Board
County Conservation District
Grant Application
Contract
No payments or project work can happen until there is a fully signed contract

## Slide 76
Ranking and Contracting
Discussion:
Ranking, Local Policy, & Contracting
Now’s the time to share materials you brought related to QAB meetings, ranking, and contracting
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette

## Slide 77
Project Life Cycle - Timing
Education and outreach
Pre-application meeting
Receive & review application
QAB meeting
CD Board meeting
Contracting
Preparing for Construction
  If applicable: Design, permitting, bidding
  Pre-construction meeting
Construction
Completion
The time of year you do these steps can make a big difference!

## Slide 78
Project Life Cycle - Timing
Education and outreach
Pre-application meeting
Receive & review application
QAB meeting
CD Board meeting
Contracting
Preparing for Construction
  If applicable: Design, permitting, bidding
  Pre-construction meeting
Construction
Completion
Annual allocations
typical timeline
Approved by SCC in May
State Budget passes 7/1
Advances available late summer/early fall
Districts have 2 years to spend funds

## Slide 79
Project Life Cycle - Timing
#1 Tip for running an effective local DGLVR Program:
Run an annual program
Where you award DGLVR grants ASAP when annual allocations are received

## Slide 80
Be ready to contract projects with new FY funds as soon as the funds are available (Fiscal Year: July 1 – June 30)
Project Life Cycle - Timing
2022 2023 2024 2025 2026 2027
FY 2025-26 funds
Use 2025 to prepare for projects that will be constructed in 2026
July 1

## Slide 81
Project Life Cycle - Timing
Jan April July Oct Jan April July Oct Jan April July Oct Jan
2025
2027
2026
Today

## Slide 82
Project Life Cycle - Timing
Jan April July Oct Jan April July Oct Jan April July Oct Jan
2025
2027
2026
Today
Pre-app meetings (start previous fall)
Contract 25-26 funds
Design, permitting, bidding
construction
Completion & final payment
QAB & CD board meetings

## Slide 83
Project Life Cycle - Timing
Jan April July Oct Jan April July Oct Jan April July Oct Jan
2025
2027
2026
Today
Pre-app meetings (start previous fall)
Contract 25-26 funds
Design, permitting, bidding
construction
Completion & final payment
QAB & CD board meetings
Contract 26-27 funds
Pre-app meetings
Apps due
Rank apps
QAB & CD board meetings
Prep for & complete construction
Completion & final payment
Notes: Sample Timeline
  Summer/Fall 2025 – Complete pre-application meetings
  Winter 2025-26 – Accept applications
  Spring 2026 – Rank project applications
  May 2026 – find out FY 25-26 allocation
  June/July 2026
    Once new allocation amount is known, hold QAB meeting and recommend projects for funding
    Approve projects at District Board meeting
    Contract the new projects with FY 25-26 funds
  July 2026 – October 2027 – Complete Construction
  November/December 2027 – Close out project including reimbursement to project participant

## Slide 84
Project Life Cycle - Timing
Jan April July Oct Jan April July Oct Jan April July Oct Jan
2025
2027
2026
Today
Contract 24-25 funds
Prep for & complete construction
Completion & final payment
QAB & CD board meetings
Pre-app meetings

## Slide 85
Project Life Cycle - Timing
Jan April July Oct Jan April July Oct Jan April July Oct Jan
2025
2027
2026
Today
Contract 24-25 funds
Prep for & complete construction
Completion & final payment
QAB & CD board meetings
Pre-app meetings
Note when contracting projects in the spring – you are about to get more funding!

## Slide 86
Project Management
Gantt Chart: a horizontal bar chart used to display the start date and duration of each task that makes up a project.
https://www.forbes.com/advisor/business/software/what-is-a-gantt-chart/
Provides quick view of:
List of tasks
Start and end dates for each task
Dependencies between tasks

## Slide 87
Project Management

## Slide 88
Project Life Cycle - Timing
Discussion:
What is your local DGLVR Program timeline?
  Deadlines – show of hands
    Once / year?
    Twice / year?
    Rolling basis?
  Pros and cons of each?
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette

## Slide 89
Preparing for Construction
Education and outreach
Pre-application meeting
Receive & review application
QAB meeting
CD Board meeting
Contracting
Preparing for Construction
  If applicable: Design, permitting, bidding
  Pre-construction meeting
Construction
Completion

## Slide 90
Choosing an engineer
Does the project need engineering or additional design?
Does the grant recipient have an engineer on staff or retainer?
What is that engineer’s specialty and are they comfortable with the type of project you’re working on?
Consider soliciting proposals for engineering services
Preparing for Construction

## Slide 91
Communicating with engineers
Provide detailed description of the work needed, including DGLVR requirements
  Pre-design meeting
  Request for Proposals (RFP) template available for DGLVR stream crossings
Require the engineer to provide district staff the design to make sure it meets DGLVR requirements
  Note CDs are not asked to do engineering on projects.
Preparing for Construction

## Slide 92
Example engineered plan review
Notes from pre-app meeting:
  Install 2 rain garden bump outs on either side of the avenue
  Use existing storm sewer inlets for overflow instead of having risers in the rain gardens
Preparing for Construction
Excerpt from engineer’s plan
Montgomery CCD
Notes: Discuss how these 2 design ideas are represented well on the plan sheet

## Slide 93
Preparing for Construction
Example engineered plan review
Notes from pre-app meeting:
  Include native plantings (including shrubs) in the rain gardens
Excerpt from engineer’s plan
Montgomery CCD
Notes: Discuss how the proposed permanent seed mixes don’t include the recommended native shrubs

## Slide 94
Preparing for Construction
Example notes to send engineer:
Overflow: It looks like the plans incorporated the CD’s recommendation to utilize the existing storm sewer system inlets as overflow instead of risers for the rain garden bump outs. Thank you.
Plantings/seed mix: The permanent seed mix listed isn’t consistent with the discussion from the pre-app meeting. We recommend adding native plantings.
  The Permanent seed mix is listed as PennDOT Formula B (flatter than 3:1 slope) and PennDOT Formula D (3:1 slope or steeper)
    Formula B info is in PennDOT Pub 408 and it appears to be grasses only for residential settings. We had difficulty finding Formula D in the Pub408 but found a 2007 Penn State factsheet listing that Formula D is for areas that will be mowed, such as medians and shoulders. Screenshots and link to the fact sheet below.
    The borough staff we met with during the pre-app meeting spoke about including native herbaceous and small shrub plantings based on their landscaping experience. We talked about things like shading and light requirements for the plants selected, etc. The borough said they didn’t want to have to do much routine maintenance on the vegetation in the rain gardens over the course of the year, so using a seed mix that is intended to be mowed wouldn’t be consistent with that plan.
Montgomery CCD
Notes: Discuss the type of feedback that can be provided to the engineer.

## Slide 95
Preparing for Construction
Montgomery CCD

## Slide 96
Permitting tips
Reach out to DEP early if you think permitting might be needed
  Include DEP in pre-app meeting or set up pre-permit app meeting
Discuss CD 105 delegation
Preparing for Construction
Photo: Monroe CCD

## Slide 97
Preparing for Construction
Discussion:
Working with Engineers/Designers
& Permitting
Now’s the time to share materials you brought related to these topics
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette

## Slide 98
Bidding – recorded webinars
April 14, 2020: Municipal Bidding
  This webinar reviewed various aspects of the municipal bidding process as it relates to municipal projects funded through the DGLVR Program. It covered an overview of the bidding process and provided additional resources.
  Webinar Download (66.3 MB): MP4 format (~ 1 hour 8 minutes)
  Presentation Downloads:
    Adobe PDF (8.81 MB)
    MS Powerpoint (16.9 MB)
June 9, 2020: COSTARS and Purchasing
  As part of the 4/14/20 “Municipal Bidding” webinar, there was some discussion and a request for more information about the COSTARS program, a cooperative purchasing program designed to make purchasing both easier and price competitive for public entities. Felicia Campbell & Kim Bullivant, two representatives from COSTARS, presented information and answered available for questions.
  Webinar Download (178 MB): MP4 format (~ 1 hour 19 minutes)
  Presentation Downloads:
    Adobe PDF (7.3 MB)
    MS Powerpoint (8.72 MB)
Preparing for Construction

## Slide 99
Bidding considerations
Each grant recipient’s experience level with bidding will vary.
Ask what their experience with bidding is and who they plan to have manage their bidding:
  Themselves, engineer, municipal services rep, etc.
Provide assistance within your comfortability level
  Ex. project narrative, prevailing wage, technical bulletins, technical specifications, completion dates
Preparing for Construction

## Slide 100
Bidding considerations
Time of year – winter/spring is best
  Bidding during the construction season is possible, but many contractors may have limited availability at that point
Amount of detail
  Need enough to get the project you want
  Not enough or too much detail will result in fewer and/or expensive bids
Preparing for Construction

## Slide 101
Bidding considerations
CDs should always review bid documents to make sure they meet DGLVR requirements
  Note that CDs do not have to oversee bidding for the grant recipient.
  Review bid docs before the bid packages go out to bidders. Make sure road owner knows this early.
Preparing for Construction

## Slide 102
Bidding considerations
  Ensure essential details in bid docs match DGLVR contract, including:
    Start/end dates
    Sketch/scope of work/quantities
    Use the DSA Request For Quote (RFQ) for DSA projects
    Road fill RFQ available as well
Preparing for Construction

## Slide 103
Bidding tips
Site showings – good ideas
  Pros/cons of mandatory site showing
  If there is a site showing, CD should always be there to answer questions pertaining to grant requirements
Preparing for Construction

## Slide 104
Bidding tips
Ask road owner to inform you ASAP when low bid is chosen.
  Consider attending the bid opening
If it’s a DSA project, find out what quarry the material is coming from and submit DSA notification to Center ASAP.
Find out the proposed construction timeframe and remind them to notify you before construction starts and update you if the schedule changes.
Preparing for Construction

## Slide 105
Preparing for Construction
Discussion:
Bidding
Now’s the time to share materials you brought related to these topics
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette

## Slide 106
For Municipal Workforce Projects
Was an annual stone bid put out and awarded for the year or was a project specific material bid completed?
When do materials need to be ordered to be onsite in time for construction?
Does equipment need to be rented?
Preparing for Construction

## Slide 107
Pre-construction Meeting
Review scope of work
Construction stakeout
Construction Schedule
Notice of Construction Start
Stabilization
Does material need to be stockpiled?
Who will coordinate with the quarry on material delivery?
Preparing for Construction

## Slide 108
Project Life Cycle
Preparing for Construction
  Done by twp labor
  Bid out materials / bid out project work
  Pre-construction meeting
    Walk site: maybe it’s been a year between pre-app and pre-con
    Flag/paint where practices will go
      Pipe inlet AND outlet locations, talk about pipe angles, headwall/endwall construction, any other stabilization

## Slide 109
Preparing for Construction
Discussion:
Pre-construction meetings
Now’s the time to share materials you brought related to these topics
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette

## Slide 110
Construction inspection
Be onsite as often as possible
  Critical Stages
  First day of construction and when practices change
Ask for paperwork/documentation as soon as it’s available
  More likely to get a copy when the grant recipient is thinking about it
  Speeds up final payment later
  Proof of permits, 811 serial number, prevailing wage documentation, DSA Certifications, etc.
Preparing for Construction
Photo: Monroe CCD

## Slide 111
Project Life Cycle - Timing
Discussion:
Construction Inspections
Working with Contractors and road crews
Now’s the time to share materials you brought related to these topics
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette

## Slide 112
Outline
Introductions
Policy Review Trivia Game
Intro to Project Management
Pre-application & application
Project administration: contracting through construction
Project completion

## Slide 113
Example Site: Dogtown Road, Genesee Twp
Final Inspection
What do you if you show up on site and see this?
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 114
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 115
Example Site: Dogtown Road, Genesee Twp
Final Inspection
What do you if you show up on site and see this?
Photo: Monroe CCD
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 116
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Discussion
Final Inspection
Does the road owner, contractor, engineer, participate?
Are there often items that need to be fixed?
How do you make sure remediation is done?
As-built notes or drawing?

## Slide 117
Example Site: Dogtown Road, Genesee Twp

## Slide 118
Example Site: Dogtown Road, Genesee Twp
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 119
Example Site: Dogtown Road, Genesee Twp
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 120
Example Site: Dogtown Road, Genesee Twp
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 121
Example Site: Dogtown Road, Genesee Twp
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 122
Example Site: Dogtown Road, Genesee Twp
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 123
Example Site: Dogtown Road, Genesee Twp
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 124
Example Site: Dogtown Road, Genesee Twp
Notes: Final inspection is required before final payment
Often easy if CD staff is on site often during construction

## Slide 125
Final paperwork
Reminder: required documentation is listed on DGLVR File Checklist
Project Completion

## Slide 126
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Discussion
Invoices
What do you look for when reviewing invoices?
Notes: Date
Supplier
Bill to/supplied to
Item
Quantity
Total price

## Slide 127
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Discussion
Invoices
Do you use an expense tracker?
Notes: Date
Supplier
Bill to/supplied to
Item
Quantity
Total price

## Slide 128
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Discussion
Invoices & Completion Report
Do you fill out the report, ask the grant recipient to fill it out, or work together on it?
Do you complete this in the field, office, or both?
What common issues do you see on invoices and encounter on the completion report?

## Slide 129
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Activity
Invoice Review
You’ve done the final inspection and now are reviewing invoices to make the final grant payment.
Review the invoices for eligibility, meeting DGLVR requirements, and consistency with construction.
Compile a list of questions/comments for the township.

## Slide 130
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Activity
Invoice Review
What issues did you find with the financial documentation?

## Slide 131
Example Site: Dogtown Road, Genesee Twp

## Slide 132
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Activity
Invoice Review
Review additional documentation

## Slide 133
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette

## Slide 134
Example Site: Dogtown Road, Genesee Twp
https://www.vhv.rs/download/TiwmRbR_graphic-picture-of-a-meeting-group-work-group/#google_vignette
Activity
Filling out the completion report
Now that the final inspection and invoice review are complete, ensure the completion report is filled out correctly.

## Slide 135
Project Completion
Generate Comp Report form in GIS
Review with road owner
Both parties sign
GIS:
  Enter final payment
  Mark project as complete

## Slide 136
Project Completion

## Slide 137
Any last questions?
Please fill out the survey!
Project Completion